## EXAMPLE Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART | [60 empty] | https://goo.gl/ejIdKR
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation |  | 309 | 309 | 0 |  |  |  |  | 100%
1.1 | Project Charter | Leon W | 40 | 40 | 0 |  | 2017-03-12 | 2017-03-15 | 4 | 100% | bar: WEEK 1 F to WEEK 2 F
1.1.1 | Project Charter Revisions | Kylie R | 25 | 25 | 0 |  | 2017-03-15 | 2017-03-16 | 2 | 100%
1.2 | Research | Pete S | 100 | 100 | 0 |  | 2017-03-15 | 2017-03-21 | 7 | 100% | bar: WEEK 2 M to WEEK 3 R
1.3 | Projections | Steve L | 60 | 60 | 0 |  | 2017-03-16 | 2017-03-22 | 7 | 100% | bar: WEEK 2 M to WEEK 3 R
1.4 | Stakeholders | Allen W | 40 | 40 | 0 |  | 2017-03-17 | 2017-03-22 | 6 | 100% | bar: WEEK 2 M to WEEK 3 R
1.5 | Guidelines | Malik M | 32 | 32 | 0 |  | 2017-03-18 | 2017-03-22 | 5 | 100% | bar: WEEK 2 M to WEEK 3 R
1.6 | Project Initiation | Malik M | 12 | 12 | 0 |  | 2017-03-23 | 2017-03-23 | 1 | 100% | bar: WEEK 3 F
2 | Project Definition and Planning |  | 210 | 110 | 100 |  |  |  |  | 52.38%
2.1 | Scope and Goal Setting | Steve L | 80 | 70 | 10 |  | 2017-03-24 | 2017-03-28 | 5 | 87.5% | bar: WEEK 4 M to WEEK 5 F
2.2 | Budget | Allen W | 60 | 40 | 20 |  | 2017-03-29 | 2017-04-02 | 5 | 66.67%
2.3 | Communication Plan | Malik M | 40 | 0 | 40 |  |  |  | 1 | 0%
2.4 | Risk Management | Malik M | 30 | 0 | 30 |  |  |  | 1 | 0%
3 | Project Launch and Execution |  | 66 | 0 | 66 |  |  |  |  | 0%
3.1 | Status and Tracking | Pete S | 20 | 0 | 20 |  |  |  | 1 | 0%
3.2 | KPIs | Leon W | 20 | 0 | 20 |  |  |  | 1 | 0%
3.2.1 | Monitoring | Kylie R | 8 | 0 | 8 |  |  |  | 1 | 0%
3.2.2 | Forecasts | Kylie R | 12 | 0 | 12 |  |  |  | 1 | 0%
3.3 | Project Updates | Pete S | 4 | 0 | 4 |  |  |  | 1 | 0%
3.3.1 | Chart Updates | Malik M | 2 | 0 | 2 |  |  |  | 1 | 0%
4 | Project Performance/Monitoring |  | 32 | 0 | 32 |  |  |  |  | 0%
4.1 | Project Objectives | Steve L | 8 | 0 | 8 |  |  |  | 1 | 0%
4.2 | Quality Deliverables | Allen W | 12 | 0 | 12 |  |  |  | 1 | 0%
4.3 | Effort and Cost Tracking | Malik M | 8 | 0 | 8 |  |  |  | 1 | 0%
4.4 | Project Performance | Malik M | 4 | 0 | 4 |  |  |  | 1 | 0%
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 617 | 419 | 198 | 60 | 10.2833 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 617 | 606.7167 | 596.4333 | 586.15 | 575.8667 | 565.5833 | 555.3 | 545.0167 | 534.7333 | 524.45 | 514.1667 | 503.8833 | 493.6 | 483.3167 | 473.0333 | 462.75 | 452.4667 | 442.1833 | 431.9 | 421.6167 | 411.3333 | 401.05 | 390.7667 | 380.4833 | 370.2 | 359.9167 | 349.6333 | 339.35 | 329.0667 | 318.7833 | 308.5 | 298.2167 | 287.9333 | 277.65 | 267.3667 | 257.0833 | 246.8 | 236.5167 | 226.2333 | 215.95 | 205.6667 | 195.3833 | 185.1 | 174.8167 | 164.5333 | 154.25 | 143.9667 | 133.6833 | 123.4 | 113.1167 | 102.8333 | 92.55 | 82.2667 | 71.9833 | 61.7 | 51.4167 | 41.1333 | 30.85 | 20.5667 | 10.2833
[10 empty] | ESTIMATE | 617 | 609 | 589 | 559 | 519 | 499 | 488 | 472 | 430 | 385 | 365 | 355 | 339 | 315 | 267 | 247 | 243 | 238 | 234 | 226 | 218 | 213 | 208 | 203 | 200 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 15968
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | WEEK 1 M: 8; WEEK 1 T: 20; WEEK 1 W: 30; WEEK 1 R: 40; WEEK 1 F: 20; WEEK 2 M: 11; WEEK 2 T: 16; WEEK 2 W: 42; WEEK 2 R: 45; WEEK 2 F: 20; WEEK 3 M: 10; WEEK 3 T: 16; WEEK 3 W: 24; WEEK 3 R: 48; WEEK 3 F: 20; WEEK 4 M: 4; WEEK 4 T: 5; WEEK 4 W: 4; WEEK 4 R: 8; WEEK 4 F: 8; WEEK 5 M: 5; WEEK 5 T: 5; WEEK 5 W: 5; WEEK 5 R: 3; WEEK 5 F: 2 | 419
[10 empty] | HRS REMAINING | 609 | 589 | 559 | 519 | 499 | 488 | 472 | 430 | 385 | 365 | 355 | 339 | 315 | 267 | 247 | 243 | 238 | 234 | 226 | 218 | 213 | 208 | 203 | 200 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 15549
CLICK HERE TO CREATE GANTT CHART TEMPLATES IN SMARTSHEET

## AD Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
SPRINT 6
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Design of project |  | 15 | 16 | -1 | 1 |  |  |  | 106.7%
1.1 | ER Schema and User stories | everyone | 4 | 4 | 0 | 1 | 2024-03-04 | 2024-03-06 | 3 | 100% | bar: WEEK 1 M to WEEK 1 W
1.2 | LoFi | everyone | 3 | 3 | 0 | 1 | 2024-03-06 | 2024-03-08 | 3 | 100% | bar: WEEK 1 W to WEEK 1 F
1.3 | Function Points | everyone | 5 | 4 | 1 | 1 | 2024-03-13 | 2024-03-14 | 2 | 80% | bar: WEEK 2 W to WEEK 2 R
1.4 | COCOMO II | everyone | 1 | 1 | 0 | 1 | 2024-03-14 | 2024-03-14 | 1 | 100% | bar: WEEK 2 R
1.5 | System architecture estimation | everyone | 1 | 2 | -1 | 1 | 2024-03-20 | 2024-03-22 | 3 | 200% | bar: WEEK 3 W; WEEK 3 F
1.6 | II Sprint definition | everyone | 1 | 2 | -1 | 1 | 2024-03-22 | 2024-03-22 | 1 | 200% | bar: WEEK 3 F
2 | Implementation of II Sprint features |  | 13 | 13 | 0 | 2 |  |  |  | 100%
2.1 | First drafting of db structure | Alessandro Catalano | 2 | 2 | 0 | 2 | 2024-03-25 | 2024-03-25 | 1 | 100% | bar: WEEK 4 M
2.2 | First drafting of frontend | Claudia Di Paolo | 3 | 3 | 0 | 2 | 2024-03-25 | 2024-03-25 | 1 | 100% | bar: WEEK 4 M
2.3 | First drafting of certification service | Saverio Dieni | 5 | 5 | 0 | 2 | 2024-03-25 | 2024-03-26 | 2 | 100% | bar: WEEK 4 M to WEEK 4 T
2.4 | Database within the docker container | Alessandro Catalano | 3 | 3 | 0 | 2 | 2024-03-27 | 2024-03-27 | 1 | 100% | bar: WEEK 4 W
2,5 | Certification service within the docker container | Saverio Dieni | 2 | 2 | 0 | 2 | 2024-03-29 | 2024-03-29 | 1 | 100% | bar: WEEK 4 F
2,6 | Signup/login Logic Part 1 | Catalano and Di paolo | 4 | 6 | -2 | 2 | 2024-03-30 | 2024-04-12 | 14 | 150% | bar: WEEK 4 F; WEEK 5 T; WEEK 6 R
2,7 | Communication between certification and recognition service | Saverio Dieni | 2 | 2 | 0 | 2 | 2024-04-02 | 2024-04-02 | 1 | 100% | bar: WEEK 4 F; WEEK 5 T
2,8 | First version of central server | Saverio Dieni | 8 | 10 | -2 | 2 | 2024-04-03 | 2024-04-05 | 3 | 125% | bar: WEEK 4 F; WEEK 5 W to WEEK 5 F
2,9 | Local db (sql file + docker) | Alessandro Catalano | 2 | 2 | 0 | 2 | 2024-04-10 | 2024-04-10 | 1 | 100% | bar: WEEK 6 W
2.10 | Certificate Image's Handling | Valerio Baldi | 3 | 10 | -7 | 2 | 2024-04-02 | 2024-04-13 | 12 | 333.3% | bar: WEEK 5 T to WEEK 5 W; WEEK 5 F; WEEK 6 W; WEEK 6 F
3 | Implementation of III Sprint features |  | 23 | 25 | -2 | 3 |  |  |  | 108.7%
3.1 | Serving frontend with docker | Alessandro Catalano | 2 | 2 | 0 | 3 | 2024-04-16 | 2024-04-16 | 1 | 100% | bar: WEEK 7 T
3.2 | Signup/Login Logic Part 2 | Everyone | 5 | 5 | 0 | 3 | 2024-04-17 | 2024-04-24 | 8 | 100% | bar: WEEK 7 W to WEEK 7 R; WEEK 8 M to WEEK 8 W
3.2.1 | user animal certificate | Saverio Dieni | 1 | 1 | 0 | 3 | 2024-04-19 | 2024-04-19 | 1 | 100% | bar: WEEK 7 F
3.2.2 | User Personal Animaldex | Valerio Baldi Saverio Dieni | 2 | 2 | 0 | 3 | 2024-04-19 | 2024-04-19 | 1 | 100% | bar: WEEK 7 F
3,3 | Signup/Login Logic Part 3 + operator table reshape | Alessandro Catalano | 4 | 4 | 0 | 3 | 2024-04-22 | 2024-04-24 | 3 | 100% | bar: WEEK 8 M to WEEK 8 W
3,4 | PersonalPage Logic redirect and data handling | Everyone | 3 | 5 | -2 | 3 | 2024-04-23 | 2024-04-24 | 2 | 166.7% | bar: WEEK 8 T to WEEK 8 W
3.5 | Complete Animaldex | Valerio Baldi | 1 | 1 | 0 | 3 | 2024-04-25 | 2024-04-25 | 1 | 100% | bar: WEEK 8 R
3,6 | Google Oauth | Valerio Baldi Saverio Dieni | 4 | 4 | 0 | 3 | 2024-04-24 | 2024-04-27 | 4 | 100% | bar: WEEK 8 W to WEEK 8 F
3.7 | Animaldex Sorting | Valerio Baldi | 1 | 1 | 0 | 3 | 2024-04-27 | 2024-04-27 | 1 | 100% | bar: WEEK 8 F
3.8 | PersonalPage Logic data displaying | Catalano Di Paolo | 3 | 3 | 0 | 3 | 2024-04-25 | 2024-04-27 | 3 | 100% | bar: WEEK 8 R to WEEK 8 F
3.9 | Animaldex Search Bar and Personaldex filter | Valerio Baldi | 2 | 2 | 0 | 3 | 2024-05-03 | 2024-05-03 | 1 | 100% | bar: WEEK 9 F
3.10 | Cookie management and integration | Saverio Dieni | 4 | 5 | -1 | 3 | 2024-05-02 | 2024-05-04 | 3 | 125% | bar: WEEK 9 W to WEEK 9 F
3.11 | Delete user account | Catalano Di Paolo | 4 | 3 | 1 | 3 | 2024-05-03 | 2024-05-03 | 1 | 75% | bar: WEEK 9 F
4 | Implementation of IV Sprint features |  | 19 | 17 | 2 | 4 |  |  |  | 89.47%
4.1 | Delete operator account | Catalano Alessandro | 1 | 1 | 0 | 4 | 2024-05-09 | 2024-05-09 | 1 | 100% | bar: WEEK 10 W
4.2 | ScoreBoard | Saverio Dieni | 2 | 2 | 0 | 4 | 2024-05-10 | 2024-05-10 | 1 | 100% | bar: WEEK 10 F to WEEK 11 F
4.3 | Updating personal info of user and operator | Catalano Alessandro | 6 | 6 | 0 | 4 | 2024-05-12 | 2024-05-12 | 1 | 100%
4.4 | Winner announcement | Saverio Dieni | 4 | 5 | -1 | 4 | 2024-05-15 | 2024-05-17 | 3 | 125%
4.5 | Adding special events | Saverio Dieni | 6 | 3 | 3 | 4 | 2024-05-21 | 2024-05-22 | 2 | 50% | bar: WEEK 12 T to WEEK 12 W
4.6 | User profile image pt1 | Catalano and Di Paolo | 8 | 6 | 2 | 4.5 | 2024-05-13 | 2024-05-13 | 1 | 75%
5 | Implementation of V Sprint features |  | 46 | 40 | 6 | 5 |  |  |  | 86.96%
5.1 | user event interaction + finish special events | Saverio Dieni | 5 | 5 | 0 | 5 | 2024-07-22 | 2024-08-03 | 13 | 100% | bar: WEEK 13 M; WEEK 14 F
5.2 | show user list for admin | Alessandro Catalano | 5 | 4 | 1 | 5 | 2024-07-30 | 2024-08-02 | 4 | 80% | bar: WEEK 14 T; WEEK 14 F
5.3 | faq page | Catalano/Di Paolo | 1 | 1 | 0 | 5 | 2024-08-02 | 2024-08-02 | 1 | 100% | bar: WEEK 14 F
5.4 | operator and user ban by admin | Alessandro Catalano | 2 | 2 | 0 | 5 | 2024-08-03 | 2024-08-03 | 1 | 100% | bar: WEEK 14 F
5.5 | Profile image pt2 and centralDB restructuring | Catalano/Di Paolo | 3 | 3 | 0 | 5 | 2024-08-05 | 2024-08-05 | 1 | 100% | bar: WEEK 15 M
5.6 | forum add comments and replies | Alessandro Catalano | 3 | 3 | 0 | 5 | 2024-08-05 | 2024-08-05 | 1 | 100% | bar: WEEK 15 M
5.7 | forum delete comments and replies by user and admin | Catalano/Di Paolo | 2 | 2 | 0 | 5 | 2024-08-06 | 2024-08-06 | 1 | 100% | bar: WEEK 15 T
5.8 | forum improved features | Alessandro Catalano | 1 | 1 | 0 | 5 | 2024-08-06 | 2024-08-06 | 1 | 100% | bar: WEEK 15 T
5.9 | modify comments and replies forum and forum filter | Catalano/Di Paolo | 3 | 2 | 1 | 5 | 2024-08-07 | 2024-08-07 | 1 | 66.67% | bar: WEEK 15 W
5.10 | Personal Map | Valerio Baldi | 2 | 3 | -1 | 5 | 2024-08-09 | 2024-08-09 | 1 | 150% | bar: WEEK 15 F
5.11 | animal emergency | Saverio Dieni | 8 | 6 | 2 | 5 | 2024-08-06 | 2024-08-09 | 4 | 75% | bar: WEEK 15 T to WEEK 15 F
5.12 | forum now on user side | Alessandro Catalano | 3 | 3 | 0 | 5 | 2024-08-11 | 2024-08-11 | 1 | 100% | bar: WEEK 16 M
5.13 | messages between users and operators | Saverio Dieni | 8 | 5 | 3 | 5 | 2024-08-20 | 2024-08-20 | 1 | 62.5% | bar: WEEK 16 T
6 | Implementation of VI Sprint features |  | 9 | 9 | 0 | 6 |  |  |  | 100%
6.1 | Emergency operator evaluation | Baldi/Dieni | 3 | 3 | 0 | 6 | 2024-08-27 | 2024-08-27 | 1 | 100% | bar: WEEK 17 T
6.2 | User evaluation | Baldi/Dieni | 1 | 1 | 0 | 6 | 2024-08-28 | 2024-08-28 | 1 | 100% | bar: WEEK 17 W
6.3 | update on changing favourite animal and displaying it | Alessandro Catalano | 2 | 2 | 0 | 6 | 2024-08-28 | 2024-08-28 | 1 | 100% | bar: WEEK 17 W
6.4 | rest mapping the report and chat microservice | Catalano/Di Paolo | 2 | 2 | 0 | 6 | 2024-08-28 | 2024-08-28 | 1 | 100% | bar: WEEK 17 W
6.5 | split change password form change credentials | Catalano | 1 | 1 | 0 | 6 | 2024-08-28 | 2024-08-28 | 1 | 100% | bar: WEEK 17 W
| BURNDOWN DATA | TOTAL HOURS | 167 | 171 | -4 | 53 | 3.1509 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 |  | HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | WEEK 1 M: 167; WEEK 1 T: 163.8491; WEEK 1 W: 160.6981; WEEK 1 R: 157.5472; WEEK 1 F: 154.3962; WEEK 2 M: 151.2453; WEEK 2 T: 148.0943; WEEK 2 W: 144.9434; WEEK 2 R: 141.7925; WEEK 2 F: 138.6415; WEEK 3 M: 135.4906; WEEK 3 T: 132.3396; WEEK 3 W: 129.1887; WEEK 3 R: 126.0377; WEEK 3 F: 122.8868; WEEK 4 M: 119.7358; WEEK 4 T: 116.5849; WEEK 4 W: 113.434; WEEK 4 R: 110.283; WEEK 4 F: 107.1321; WEEK 5 M: 103.9811; WEEK 5 T: 100.8302; WEEK 5 W: 97.6792; WEEK 5 R: 94.5283; WEEK 5 F: 91.3774; WEEK 6 M: 88.2264; WEEK 6 T: 85.0755; WEEK 6 W: 81.9245; WEEK 6 R: 78.7736; WEEK 6 F: 75.6226; WEEK 7 M: 72.4717; WEEK 7 T: 69.3208; WEEK 7 W: 66.1698; WEEK 7 R: 63.0189; WEEK 7 F: 59.8679; WEEK 8 M: 56.717; WEEK 8 T: 53.566; WEEK 8 W: 50.4151; WEEK 8 R: 47.2642; WEEK 8 F: 44.1132; WEEK 9 M: 40.9623; WEEK 9 T: 37.8113; WEEK 9 W: 34.6604; WEEK 9 R: 31.5094; WEEK 9 F: 28.3585; WEEK 10 M: 25.2075; WEEK 10 T: 22.0566; WEEK 10 W: 18.9057; WEEK 10 R: 15.7547; WEEK 10 F: 12.6038; WEEK 11 M: 9.4528; WEEK 11 T: 6.3019; WEEK 11 W: 3.1509
[10 empty] | ESTIMATE | 167 | 166 | 165 | 162 | 161 | 160 | 158 | 155 | 154 | 153 | 150 | 143 | 140 | 137 | 129 | 123 | 118 | 116 | 112 | 108 | 106 | 104 | 102 | 101 | 100 | 97 | 94 | 89 | 84 | 80 | 76 | 74 | 72 | 66 | 65 | 63 | 53 | 51 | 49 | 48 | 46 | 45 | 42 | 40 | 33 | 27 | 22 | 18 | 17 | 13 | 10 | 5 | 2 |  | 4771
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 3 | 7 | 3 | 3 | 8 | 6 | 5 | 2 | 4 | 4 | 2 | 2 | 2 | 1 | 1 | 3 | 3 | 5 | 5 | 4 | 4 | 2 | 2 | 6 | 1 | 2 | 10 | 2 | 2 | 1 | 2 | 1 | 3 | 2 | 7 | 6 | 5 | 4 | 1 | 4 | 3 | 5 | 3 | 6 |  | 171
[10 empty] | HRS REMAINING | 166 | 165 | 162 | 161 | 160 | 158 | 155 | 154 | 153 | 150 | 143 | 140 | 137 | 129 | 123 | 118 | 116 | 112 | 108 | 106 | 104 | 102 | 101 | 100 | 97 | 94 | 89 | 84 | 80 | 76 | 74 | 72 | 66 | 65 | 63 | 53 | 51 | 49 | 48 | 46 | 45 | 42 | 40 | 33 | 27 | 22 | 18 | 17 | 13 | 10 | 5 | 2 | -4 |  | 4600
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SPRINT | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | STATUS KEY | WORK ESTIMATE IN HOURS
2 e 3 | user login | as a user I want to login to the website using the info provided during the registration | User Management (Di Paolo/Catalano) |  | Completed | Not Started | 1
2 e 3 | operator deletion | as an operator I want to delete my account | User Management (Di Paolo/Catalano) |  | Completed | In Progress | 2
2 e 3 | user registration | as a user I want to register to the website | User Management (Di Paolo/Catalano) |  | Completed | Completed | 4
2 e 3 | operator login | as an operator I want to login to the website using the info provided during the registration | User Management (Di Paolo/Catalano) |  | Completed |  | 8
2 e 3 | operator registration | as an operator I want to register to the website | User Management (Di Paolo/Catalano) |  | Completed |  | 16
2 | user oauth | as a user I want to register with my google account | User Management (Baldi/Dieni) |  | Completed |  | 24
2 | user agreement | as a user or third party authority I want to be able to be informed on how my data is handled by the application and their owners | User Management (Di Paolo/Catalano) |  | Completed |  | 40
3 | user deletion | as a user I want to delete my account | User Management (Di Paolo/Catalano) |  | Completed |  | 80
3, 4, 5 | users list | as an admin I want to see the list of all users | User Management (Di Paolo/Catalano) |  | Completed
2, 3 | user achievement | as a user I want to unlock animal description once the certificate has been uploaded | Certification (Baldi/Dieni) |  | Completed
3 | user personal animaldex | as a user I want to see my personal animaldex with my certificates | Certification (Baldi/Dieni) |  | Completed
3 | animaldex search | as a user I want to look for a specific animal in the animaldex using the search bar in the page | Certifcation (Baldi/Dieni) |  | Completed
2 e 3 | user animal certificate | as a user I want to upload/update a photo certifiyng the encounter of the animal in order to obtain points | Certifcation (Baldi/Dieni) |  | Completed
3 | user complete animaldex sorting | as a user I want to sort the complete list of animals | DB/Certification (Baldi/Dieni) |  | Completed
2 e 3 | user complete animaldex | as a user I want to view the complete list of all the animals in the database | DB (Baldi/Dieni) |  | Completed
2 e 3 | animal positions | as a user I want to discover known positions of an animal | DB (Baldi/Dieni) |  | Completed
4, 5 | user profile photo modification | as a user I want to change my profile photo | User Management/DB/Frontend (Di Paolo/Catalano) |  | Completed
4 | user credentials and personal info | as a user I want to edit my personal info and change my credentials associated to my account | User Management (Di Paolo/Catalano) |  | Completed
4, 5 | admin ban | as an admin I want to ban not conforming users or emergency operators (delete their account) | User Management (Di Paolo/Catalano) |  | Completed
4, 5 | user preferencies | as a user I want to define my preferences on favourite animal | User Management (Di Paolo/Catalano) |  | Completed
4 | winner announcement | as a user on the ranking podium after a season I'm gaining a badge on my profile | Certification/User Management (Baldi/Dieni) |  | Completed
4, 5 | user map | as a user I want to view the homepage map divided by areas | Certification/Frontend (Baldi/Dieni) |  | Completed
4, 5 | admin events | as an admin I want to add temporary events that allow users to gain more points | Certification (Baldi/Dieni) |  | Completed
4, 5 | user competition | as a user I want to check my score on the competition scoreboard | Certification (Baldi/Dieni) |  | Completed
4 | user event interaction | as a user I want to be able to participate to special events and gain more points | Certification (Baldi/Dieni) |  | Completed
5 | operator notifications | as an emergency operator I want to receive notifications from users | Notification(Dieni/Baldi) |  | Completed
5 | user issues | as a user I want to seek for help in the FAQ section | Frontend (Di Paolo/Catalano) |  | Completed
5 | user evaluation | as an emergency operator I want to evaluate the reliability of the user | Notification(Dieni/Baldi) |  | Completed
5 | operator response | as an emergency operator I want to send updates on the user help request | Notification (Dieni/Baldi/Catalano/Di Paolo) |  | Completed
5 | emergency operator evaluation | as a user I want to evaluate the reliability of the emergency operator | Notification(Dieni/Baldi) |  | Completed
5 | message deletion | as a user or an operator I want to delete previous messages | Notification(Dieni/Baldi) |  | Completed
5 | emergency chat | as a user or an operator I want to read and write messages | Notification(Dieni/Baldi) |  | Completed
5 | animal emergency | as a user I want to report if I meet a hurt animal and call for emergency | Notification(Dieni/Baldi) |  | Completed
5 | user modifying and deleting comments | as a user I want to modify and delete my own comments on the forum | Forum (Di Paolo/Catalano) |  | Completed
5 | admin delete comments | as an admin I want to delete comments on the forum | Forum (Di Paolo/Catalano) |  | Completed
5 | user comments | as a user I want to take part to the forum, by adding a comment or replying to an existing comment | Forum (Di Paolo/Catalano) |  | Completed
5 | user forum filter | as a user I want to filter the posts in the forum by certain condition | Forum (Di Paolo/Catalano) |  | Completed

## User Stories or Tasks
SCRUM PROJECT MANAGEMENT GANTT CHART
USER STORIES or TASKS
TASK TITLE | TASK DESCRIPTION | COMPONENT | PRIORITY | ADDED BY | DATED ADDED
user achievement | as a user I want to unlock animal description once the certificate has been uploaded | Certification |  | alessandro | 2024-03-03
user map | as a user I want to view the homepage map divided by areas | Certification/Frontend |  | alessandro | 2024-03-03
admin report | as an admin I want to check the reports and block or delete users | Notification/User Management/Forum |  | alessandro | 2024-03-03
user login | as a user I want to login to the website using the info provided during the registration | User Management |  | alessandro | 2024-03-03
user credentials and personal info | as a user I want to edit my personal info and change my credentials associated to my account | User Management |  | alessandro | 2024-03-03
user animal certificate | as a user I want to upload/update a photo certifiyng the encounter of the animal in order to obtain points | Certifcation |  | claudia | 2024-03-03
winner announcement | as a user on the ranking podium after a season I'm gaining a badge on my profile | Certification/User Management |  | claudia | 2024-03-03
user complete animaldex | as a user I want to view the complete list of all the animals in the database | DB |  | claudia | 2024-03-03
user registration | as a user I want to register to the website | User Management |  | claudia | 2024-03-03
admin events | as an admin I want to add temporary events that allow users to gain more points | Certification |  | saverio | 2024-03-03
user complete animaldex sorting | as a user I want to sort the complete list of animals | DB/Certification |  | saverio | 2024-03-03
user comments | as a user I want to take part to the forum, by adding a comment or replying to an existing comment | Forum |  | saverio | 2024-03-03
user oauth | as a user I want to register with my google account | User Management |  | saverio | 2024-03-03
user profile photo modification | as a user I want to change my profile photo | User Management/DB/Frontend |  | saverio | 2024-03-03
user competition | as a user I want to check my score on the competition scoreboard | Certification |  | valerio | 2024-03-03
user forum filter | as a user I want to filter the posts in the forum by certain condition | Forum |  | valerio | 2024-03-03
user deletion | as a user I want to delete my account | User Management |  | valerio | 2024-03-03
user preferencies | as a user I want to define my preferences on favourite animal and notifications about comments and operators | User Management |  | valerio | 2024-03-03
user report | as a user I want to report other users who misbehave | User Management |  | valerio | 2024-03-03
animaldex search | as a user I want to look for a specific animal in the animaldex using the search bar in the page | Certifcation |  | alessandro | 2024-03-06
user modifying comments | as a user I want to modify my own comments on the forum | Forum |  | alessandro | 2024-03-06
operator notifications | as an emergency operator I want to receive notifications from users | Notification |  | alessandro | 2024-03-06
user credentials | as a user I want to be able to recover my credentials | User Management |  | alessandro | 2024-03-06
operator deletion | as an operator I want to delete my account | User Management |  | alessandro | 2024-03-06
admin ban | as an admin I want to ban user or emergency operator that has a certain amount of negative evaluations | User Management |  | alessandro | 2024-03-06
admin modifying comments | as an admin I want to modify/delete all comments on the forum | Forum |  | claudia | 2024-03-06
user issues | as a user I want to ask for help by reporting my issue to an admin | Notification |  | claudia | 2024-03-06
user evaluation | as an emergency operator I want to evaluate the reliability of the user | Notification |  | claudia | 2024-03-06
operator login | as an operator I want to login to the website using the info provided during the registration | User Management |  | claudia | 2024-03-06
operator registration | as an operator I want to register to the website | User Management |  | claudia | 2024-03-06
certificates via google | as a user I want to upload a certificate from google photos/drive | Certificate |  | saverio | 2024-03-06
operator response | as an emergency operator I want to send updates on the user help request | Notification |  | saverio | 2024-03-06
emergency operator evaluation | as a user I want to evaluate the reliability of the emergency operator | Notification |  | saverio | 2024-03-06
admin notifications | as an admin I want to receive the evaluation of both the user and the emergency operator | Notification |  | saverio | 2024-03-06
user agreement | as a user or third party authority I want to be able to be informed on how my data is handled by the application and their owners | User Management |  | saverio | 2024-03-06
user personal animaldex | as a user I want to see my personal animaldex with my certificates | Certification |  | valerio | 2024-03-06
user event interaction | as a user I want to be able to participate to special events and gain more points | Certification |  | valerio | 2024-03-06
animal positions | as a user I want to discover known positions of an animal | DB |  | valerio | 2024-03-06
animal emergency | as a user I want to report if I meet a hurt animal and call for emergency | Notification |  | valerio | 2024-03-06
users list | as an admin I want to see the list of all users | User Management |  | valerio | 2024-03-06
emergency chat | as a user or an operator I want to read and write messages | Notification |  | claudia | 2024-08-27
message deletion | as a user or an operator I want to delete previous messages | Notification |  | valerio | 2024-08-27