## EXAMPLE Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART | [60 empty] | https://goo.gl/ejIdKR
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation |  | 309 | 309 | 0 |  |  |  |  | 100%
1.1 | Project Charter | Leon W | 40 | 40 | 0 |  | 2017-03-12 | 2017-03-15 | 4 | 100% | bar: WEEK 1 F to WEEK 2 F
1.1.1 | Project Charter Revisions | Kylie R | 25 | 25 | 0 |  | 2017-03-15 | 2017-03-16 | 2 | 100%
1.2 | Research | Pete S | 100 | 100 | 0 |  | 2017-03-15 | 2017-03-21 | 7 | 100% | bar: WEEK 2 M to WEEK 3 R
1.3 | Projections | Steve L | 60 | 60 | 0 |  | 2017-03-16 | 2017-03-22 | 7 | 100% | bar: WEEK 2 M to WEEK 3 R
1.4 | Stakeholders | Allen W | 40 | 40 | 0 |  | 2017-03-17 | 2017-03-22 | 6 | 100% | bar: WEEK 2 M to WEEK 3 R
1.5 | Guidelines | Malik M | 32 | 32 | 0 |  | 2017-03-18 | 2017-03-22 | 5 | 100% | bar: WEEK 2 M to WEEK 3 R
1.6 | Project Initiation | Malik M | 12 | 12 | 0 |  | 2017-03-23 | 2017-03-23 | 1 | 100% | bar: WEEK 3 F
2 | Project Definition and Planning |  | 210 | 110 | 100 |  |  |  |  | 52.38%
2.1 | Scope and Goal Setting | Steve L | 80 | 70 | 10 |  | 2017-03-24 | 2017-03-28 | 5 | 87.5% | bar: WEEK 4 M to WEEK 5 F
2.2 | Budget | Allen W | 60 | 40 | 20 |  | 2017-03-29 | 2017-04-02 | 5 | 66.67%
2.3 | Communication Plan | Malik M | 40 | 0 | 40 |  |  |  | 1 | 0%
2.4 | Risk Management | Malik M | 30 | 0 | 30 |  |  |  | 1 | 0%
3 | Project Launch and Execution |  | 66 | 0 | 66 |  |  |  |  | 0%
3.1 | Status and Tracking | Pete S | 20 | 0 | 20 |  |  |  | 1 | 0%
3.2 | KPIs | Leon W | 20 | 0 | 20 |  |  |  | 1 | 0%
3.2.1 | Monitoring | Kylie R | 8 | 0 | 8 |  |  |  | 1 | 0%
3.2.2 | Forecasts | Kylie R | 12 | 0 | 12 |  |  |  | 1 | 0%
3.3 | Project Updates | Pete S | 4 | 0 | 4 |  |  |  | 1 | 0%
3.3.1 | Chart Updates | Malik M | 2 | 0 | 2 |  |  |  | 1 | 0%
4 | Project Performance/Monitoring |  | 32 | 0 | 32 |  |  |  |  | 0%
4.1 | Project Objectives | Steve L | 8 | 0 | 8 |  |  |  | 1 | 0%
4.2 | Quality Deliverables | Allen W | 12 | 0 | 12 |  |  |  | 1 | 0%
4.3 | Effort and Cost Tracking | Malik M | 8 | 0 | 8 |  |  |  | 1 | 0%
4.4 | Project Performance | Malik M | 4 | 0 | 4 |  |  |  | 1 | 0%
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 617 | 419 | 198 | 60 | 10.2833 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 617 | 606.7167 | 596.4333 | 586.15 | 575.8667 | 565.5833 | 555.3 | 545.0167 | 534.7333 | 524.45 | 514.1667 | 503.8833 | 493.6 | 483.3167 | 473.0333 | 462.75 | 452.4667 | 442.1833 | 431.9 | 421.6167 | 411.3333 | 401.05 | 390.7667 | 380.4833 | 370.2 | 359.9167 | 349.6333 | 339.35 | 329.0667 | 318.7833 | 308.5 | 298.2167 | 287.9333 | 277.65 | 267.3667 | 257.0833 | 246.8 | 236.5167 | 226.2333 | 215.95 | 205.6667 | 195.3833 | 185.1 | 174.8167 | 164.5333 | 154.25 | 143.9667 | 133.6833 | 123.4 | 113.1167 | 102.8333 | 92.55 | 82.2667 | 71.9833 | 61.7 | 51.4167 | 41.1333 | 30.85 | 20.5667 | 10.2833
[10 empty] | ESTIMATE | 617 | 609 | 589 | 559 | 519 | 499 | 488 | 472 | 430 | 385 | 365 | 355 | 339 | 315 | 267 | 247 | 243 | 238 | 234 | 226 | 218 | 213 | 208 | 203 | 200 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 15968
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | WEEK 1 M: 8; WEEK 1 T: 20; WEEK 1 W: 30; WEEK 1 R: 40; WEEK 1 F: 20; WEEK 2 M: 11; WEEK 2 T: 16; WEEK 2 W: 42; WEEK 2 R: 45; WEEK 2 F: 20; WEEK 3 M: 10; WEEK 3 T: 16; WEEK 3 W: 24; WEEK 3 R: 48; WEEK 3 F: 20; WEEK 4 M: 4; WEEK 4 T: 5; WEEK 4 W: 4; WEEK 4 R: 8; WEEK 4 F: 8; WEEK 5 M: 5; WEEK 5 T: 5; WEEK 5 W: 5; WEEK 5 R: 3; WEEK 5 F: 2 | 419
[10 empty] | HRS REMAINING | 609 | 589 | 559 | 519 | 499 | 488 | 472 | 430 | 385 | 365 | 355 | 339 | 315 | 267 | 247 | 243 | 238 | 234 | 226 | 218 | 213 | 208 | 203 | 200 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 15549
CLICK HERE TO CREATE GANTT CHART TEMPLATES IN SMARTSHEET

## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Design of project |  | 10 | 10 | 0 |  |  |  |  | 100%
1.1 | User stories |  | 4 | 4 | 0 |  | 2024-03-04 | 2024-03-06 | 3 | 100% | bar: WEEK 1 M to WEEK 1 W
1.1.1 | LoFi |  | 3 | 3 | 0 |  | 2024-03-06 | 2024-03-08 | 3 | 100% | bar: WEEK 1 W to WEEK 2 F
1.2 | Function Points |  | 3 | 3 | 0 |  | 2024-03-13 | 2024-03-13 | 1 | 100%
1.3 | COCOMO II |  |  |  | 0 |  |  |  | 1 | #DIV/0!
1.4 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
1.5 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
1.6 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
2 | SCRUM definition |  | 0 | 0 | 0 |  |  |  |  | #DIV/0!
2.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0! | bar: WEEK 4 M
2.2 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
2.3 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
2.4 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3 |  |  | 0 | 0 | 0 |  |  |  |  | #DIV/0!
3.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0! | bar: WEEK 7 M
3.2 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3.2.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3.2.2 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3.3 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3.3.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
4 |  |  | 0 | 0 | 0 |  |  |  |  | #DIV/0!
4.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0! | bar: WEEK 10 M
4.2 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
4.3 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
4.4 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 10 | 10 | 0 | 60 | 0.16667 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 10 | 9.8333 | 9.6667 | 9.5 | 9.3333 | 9.1667 | 9 | 8.8333 | 8.6667 | 8.5 | 8.3333 | 8.1667 | 8 | 7.8333 | 7.6667 | 7.5 | 7.3333 | 7.1667 | 7 | 6.8333 | 6.6667 | 6.5 | 6.3333 | 6.1667 | 6 | 5.8333 | 5.6667 | 5.5 | 5.3333 | 5.1667 | 5 | 4.8333 | 4.6667 | 4.5 | 4.3333 | 4.1667 | 4 | 3.8333 | 3.6667 | 3.5 | 3.3333 | 3.1667 | 3 | 2.8333 | 2.6667 | 2.5 | 2.3333 | 2.1667 | 2 | 1.8333 | 1.6667 | 1.5 | 1.3333 | 1.1667 | 1 | 0.83333 | 0.66667 | 0.5 | 0.33333 | 0.16667
[10 empty] | ESTIMATE | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 600
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | [60 empty] | 0
[10 empty] | HRS REMAINING | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 600
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
[6 empty] | 1 | Not Started |  | Not Started | 1
[6 empty] | 2 | In Progress |  | In Progress | 2
[6 empty] | 8 | Completed |  | Completed | 4
[6 empty] | 8 | Not Started |  |  | 8
[6 empty] | 4 |  |  |  | 16
[6 empty] | 80 |  |  |  | 24
[6 empty] | 16 |  |  |  | 40
[6 empty] | 8 |  |  |  | 80
4
2
24
40
8

## User Stories or Tasks
SCRUM PROJECT MANAGEMENT GANTT CHART
USER STORIES or TASKS
TASK TITLE | TASK DESCRIPTION | ADDED BY | DATED ADDED
user registration | as a user I want to register to the website | claudia | 2024-03-03
user login | as a user I want to login to the website using the info provided during the registration | alessandro | 2024-03-03
user deletion | as a user I want to delete my account | valerio | 2024-03-03
user oauth | as a user I want to register with my google account | saverio | 2024-03-03
user profile photo modification | as a user I want to change my profile photo | saverio | 2024-03-03
user credentials and personal info | as a user I want to edit my personal info and change my credentials associated to my account | alessandro | 2024-03-03
user preferencies | as a user I want to define my preferences on favourite animal and notifications | valerio | 2024-03-03
user upload animal certificate | as a user I want to upload a photo certifiyng the encounter of the animal in order to obtain points | claudia | 2024-03-03
user competition | as a user I want to check my score on the competition scoreboard | valerio | 2024-03-03
user achievement | as a user I want to unlock animal description once the certificate has been uploaded | alessandro | 2024-03-03
user comments | as a user I want to take part to the forum and express my opinion towards a specific topic | saverio | 2024-03-03
user like/dislike | as a user I want to express like or dislike on a content | claudia | 2024-03-03
user report | as a user I want to report other users who misbehave | valerio | 2024-03-03
admin report | as an admin I want to check the reports and block or delete users | alessandro | 2024-03-03
admin events | as an admin I want to add temporary events that allow users to gain more points | saverio | 2024-03-03
winner announcement | as a user on the ranking podium after a season I'm gaining a badge on my profile | claudia | 2024-03-03
user interactive map | as a user I want to view the interactive homepage map divided by areas | alessandro | 2024-03-03
user forum filter | as a user I want to filter the posts in the forum by certain condition | valerio | 2024-03-03
user personal animaldex | as a user I want to see my personal animaldex with my certificates | valerio | 2024-03-06
user complete animaldex | as a user I want to view the complete list of all the animals in the database | claudia | 2024-03-03
user complete animaldex sorting | as a user I want to sort the complete list of animals | saverio | 2024-03-03
user issues | as a user I want to ask for help by sending an email to the help center reporting my issue | claudia | 2024-03-06
animal positions | as a user I want to discover known positions of an animal | valerio | 2024-03-06
user credentials | as a user I want to be able to recover my credentials | alessandro | 2024-03-06
certificates via google | as a user I want to upload a certificate from google photos/drive | saverio | 2024-03-06
user modifying comments | as a user I want to modify my own comments on the forum | alessandro | 2024-03-06
admin modifying comments | as an admin I want to modify/delete all comments on the forum | claudia | 2024-03-06
users list | as an admin I want to see the list of all users | valerio | 2024-03-06
user agreement | as a user or third party authority I want to be able to be informed on how my data is handled by the application and their owners | saverio | 2024-03-06
animal emergency | as a user I want to report if I meet a hurt animal and call for emergency | valerio | 2024-03-06
operator notifications | as an emergency operator I want to receive notifications from users | alessandro | 2024-03-06
operator response | as an emergency operator I want to send updates on the user help request | saverio | 2024-03-06
operator login | as an operator I want to login to the website using the info provided during the registration | claudia | 2024-03-06
operator deletion | as an operator I want to delete my account | alessandro | 2024-03-06
operator registration | as an operator I want to register to the website | claudia | 2024-03-06
user event interaction | as a user I want to be able to participate to special events and gain more points | valerio | 2024-03-06
emergency operator evaluation | as a user I want to evaluate the reliability of the emergency operator | saverio | 2024-03-06
user evaluation | as an emergency operator I want to evaluate the reliability of the user | claudia | 2024-03-06
admin notifications | as an admin I want to receive the evaluation of both the user and the emergency operator | saverio | 2024-03-06
admin ban | as an admin I want to ban user or emergency operator that has a certain amount of negative evaluations | alessandro | 2024-03-06
animaldex search | as a user I want to look for a specific animal in the animaldex using the search bar in the page | alessandro | 2024-03-06